## Work Steps Updated
| Must Complete by | 2026-01-13
| Order Quantity | 400
|  | Time (sec/piece) | Output/Hour | Total Time (sec) | Total Time (min) | Total Time (hours)
| 1. CUTTING: | 97 | 37.1134 | 38800 | 646.6667 | 10.7778
﻿﻿﻿Fabric:
| Cut the fabric panels. 18s (just cut time, no set-up) | 90 | 40 | 36000 | 600 | 10
﻿﻿﻿Trim:
| I. Cut the Velcro pieces. 2s | 2 | 1800 | 800 | 13.3333 | 0.22222
| II. Cut the zipper. 5s | 5 | 720 | 2000 | 33.3333 | 0.55556
Step 1 must be complete prior to step 2 | 2. SILKSCREEN: | 0 | #DIV/0! | 0 | 0 | 0
| A. N/A | 0 | #DIV/0! | 0 | 0 | 0
| 3. PREP STEPS: | 7 | 514.2857 | 2800 | 46.6667 | 0.77778
| A. Sew the USA flag onto the fabric panel. 7s | 7 | 514.2857 | 2800 | 46.6667 | 0.77778
Dependent on complettion of 1, 2 | 4. SEWING: | 654 | 3686.1933 | 261600 | 4360 | 72.6667
| A. Small Velcro Pocket | 45 | 324 | 18000 | 300 | 5
| I. Hem the short edges. 20s | 20 | 180 | 8000 | 133.3333 | 2.2222
| Il. Sew on the hook Velcro. 25s | 25 | 144 | 10000 | 166.6667 | 2.7778
| B. Connector Strap | 140 | 1059.4286 | 56000 | 933.3333 | 15.5556
| I. Sew the panel together along the one long side. 12s | 12 | 300 | 4800 | 80 | 1.3333
| Il. Turn inside-out. 28s | 28 | 128.5714 | 11200 | 186.6667 | 3.1111
| III. Sew the 2 sides of the connector strap panel. 25s | 25 | 144 | 10000 | 166.6667 | 2.7778
| IV. Sew the connector strap to the small Velcro pocket, add the loop Velcro. 35s | 35 | 102.8571 | 14000 | 233.3333 | 3.8889
| V. Close the sides of the small Velcro pocket and cut corners. 15s | 15 | 240 | 6000 | 100 | 1.6667
| VI. Cut threads turn pocket right side out 25s | 25 | 144 | 10000 | 166.6667 | 2.7778
Dependent on complettion of 3 | C. Hanging big pocket | 127 | 1599.6218 | 50800 | 846.6667 | 14.1111
| I. Hem long side. 17s | 17 | 211.7647 | 6800 | 113.3333 | 1.8889
| Il. Fold to the marking, and close both sides. 35s | 35 | 102.8571 | 14000 | 233.3333 | 3.8889
| IlI. Add stitching to the lower corners to create volume turn right side out. 36s | 15 | 240 | 6000 | 100 | 1.6667
| IV. Turn Right Side out | 16 | 225 | 6400 | 106.6667 | 1.7778
| V. Sew the center stitch. Had to fold material to find center (NOT MARKED) 20s | 20 | 180 | 8000 | 133.3333 | 2.2222
| VI. Add straight single-stitching to the top of the pocket. 15s | 15 | 240 | 6000 | 100 | 1.6667
| VII. Stitch the connector strap to the large pocket. 9s | 9 | 400 | 3600 | 60 | 1
Dependent on complettion of A, B & C | D. Cushion cover | 208 | 416 | 83200 | 1386.6667 | 23.1111
| I. Sew the zipper onto the 2 fabric panels. 100s | 100 | 36 | 40000 | 666.6667 | 11.1111
| Il. Cut off extra material and add the zipper pull. 30s | 30 | 120 | 12000 | 200 | 3.3333
| III. Add closing stitch to both zipper ends. Cut thread. 18s | 18 | 200 | 7200 | 120 | 2
| IV. Sew together Big Hanging Pocket and Connector Strap and Zipper panels. 60s | 60 | 60 | 24000 | 400 | 6.6667
Dependent on complettion of D | E. Finishing: | 134 | 287.1429 | 53600 | 893.3333 | 14.8889
| I. Sew on the side panels. 120s | 120 | 30 | 48000 | 800 | 13.3333
| II. Add ZigZag to the top of the hanging big pocket. 14s | 14 | 257.1429 | 5600 | 93.3333 | 1.5556
Dependent on Completetion of E | 5. INSPECTION: | 170 | 372 | 68000 | 1133.3333 | 18.8889
| ﻿﻿﻿Clean and inspect inside. 30s | 30 | 120 | 12000 | 200 | 3.3333
| Turn right side out. 50s | 50 | 72 | 20000 | 333.3333 | 5.5556
| ﻿﻿﻿Insert the foam piece into the headrest. 30s | 30 | 120 | 12000 | 200 | 3.3333
| ﻿﻿﻿Pack. 60s | 60 | 60 | 24000 | 400 | 6.6667
| TOTAL | 928 |  | 371200 | 6186.6667 | 103.1111
| TOTAL (without CUTTING & SILKSCREEN) | 831 |  | 332400 | 5540 | 92.3333
| Total Days to complete Job | 2
| TOTAL Number of Resources | 5
| Number of Hours required per person | 18.4667
| Total Hours/Day/Person | 9.2333
| Total Overtime per day | 2.2333

## Production Steps
| Monday - 1/12/20225 | [6 empty] | Tuesday - 1/13/20225 | [6 empty] | Wednesday - 1/14/20225 | [6 empty] | Thursday - 1/15/20225 | [6 empty] | Friday - 1/16/20225 | [6 empty] | Saturday - 1/17/20225 | [6 empty] | Monday - 1/19/20225 |  |  |  | Tuesday - 1/20/20225
| Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Names | # of People | Day Output | Total Output | Names | # of People | Day Output | Total Output
1. CUTTING:
﻿﻿﻿Fabric:
Cut the fabric panels. 18s (just cut time, no set-up)
﻿﻿﻿Trim:
I. Cut the Velcro pieces. 2s
II. Cut the zipper. 5s
2. SILKSCREEN:
A. N/A
3. PREP STEPS:
A. Sew the USA flag onto the fabric panel. 7s | A - Sewing | 0.77778 | 1 | 10:00 | 10:47 |  |  | X - Sewing | 0.77778 | 1 | 10:00 | 10:47
4. SEWING:
A. Small Velcro Pocket
I. Hem the short edges. 20s | B - Sewing | 2.2222 | 1 | 10:00 | 12:43 | [9 empty] | B - Sewing | 2.2222 | 1 | 7:00 | 9:43
Il. Sew on the hook Velcro. 25s | B - Sewing | 2.7778 | 1 | 12:48 | 15:35 | [9 empty] | B - Sewing | 2.7778 | 1 | 9:48 | 13:05
B. Connector Strap
I. Sew the panel together along the one long side. 12s | C - Sewing | 1.3333 | 1 | 10:00 | 11:50 | [9 empty] | C - Sewing | 1.3333 | 1 | 7:00 | 8:20
Il. Turn inside-out. 28s | F & G - Other | 3.1111 | 2 | 10:00 | 12:03 | [9 empty] | F & G - Other | 3.1111 | 2 | 7:00 | 8:33
III. Sew the 2 sides of the connector strap panel. 25s | C & A - Sewing | 2.7778 | 2 | 11:55 | 13:18 | [9 empty] | C & A - Sewing | 2.7778 | 2 | 8:25 | 9:48
IV. Sew the connector strap to the small Velcro pocket, add the loop Velcro. 35s | C & A - Sewing | 3.8889 | 2 | 13:23 | 15:20 | [9 empty] | C & A - Sewing | 3.8889 | 2 | 8:38 | 10:35
V. Close the sides of the small Velcro pocket and cut corners. 15s | B, C & A - Sewing | 1.6667 | 3 | 15:25 | 15:58 | [9 empty] | C & A - Sewing | 1.6667 | 2 | 9:53 | 10:43
VI. Cut threads turn pocket right side out 25s | B, C & A - Sewing | 2.7778 | 3 | 16:03 | 16:59 | [9 empty] | C & A - Sewing | 2.7778 | 2 | 10:40 | 12:33
C. Hanging big pocket
I. Hem long side. 17s | D & E - Sewing | 1.8889 | 2 | 10:00 | 11:27 | [9 empty] | D & E - Sewing | 1.8889 | 2 | 7:00 | 8:27
Il. Fold to the marking, and close both sides. 35s | D & E - Sewing | 3.8889 | 2 | 11:32 | 13:28 | [9 empty] | D & E - Sewing | 3.8889 | 2 | 8:32 | 10:28
IlI. Add stitching to the lower corners to create volume turn right side out. 36s | D & E - Sewing | 1.6667 | 2 | 13:33 | 14:23 | [9 empty] | D & E - Sewing | 1.6667 | 2 | 10:33 | 11:53
IV. Turn Right Side out | F & G - Other | 1.7778 | 2 | 13:33 | 14:27 | [9 empty] | F & G - Other | 1.7778 | 2 | 10:33 | 11:57
V. Sew the center stitch. Had to fold material to find center (NOT MARKED) 20s | D & E - Sewing | 2.2222 | 2 | 14:28 | 15:35 | [9 empty] | D & E - Sewing | 2.2222 | 2 | 11:58 | 13:05
VI. Add straight single-stitching to the top of the pocket. 15s | D & E - Sewing | 1.6667 | 2 | 15:40 | 16:30 | [9 empty] | A, C, D & E - Sewing | 1.6667 | 3 | 12:02 | 12:35
VII. Stitch the connector strap to the large pocket. 9s | D & E - Sewing | 1 | 2 | 16:35 | 17:05 | [9 empty] | A, C, D & E - Sewing | 1 | 4 | 13:10 | 13:25
D. Cushion cover
I. Sew the zipper onto the 2 fabric panels. 100s | [7 empty] | A, B, C, D & E - Sewing | 11.1111 | 5 | 7:00 | 9:13 |  |  | A, B, C, D & E - Sewing | 11.1111 | 5 | 1:30 | 3:43
Il. Cut off extra material and add the zipper pull. 30s | [7 empty] | A, B, C, D & E - Sewing | 3.3333 | 5 | 9:18 | 9:58 |  |  | A, B, C, D & E - Sewing | 3.3333 | 5 | 3:48 | 4:28
III. Add closing stitch to both zipper ends. Cut thread. 18s | [7 empty] | A, B, C, D & E - Sewing | 2 | 5 | 10:03 | 10:27 | [9 empty] | A, B, C, D & E - Sewing | 2 | 5 | 7:00 | 7:24
IV. Sew together Big Hanging Pocket and Connector Strap and Zipper panels. 60s | [7 empty] | A, B, C, D & E - Sewing | 6.6667 | 5 | 10:32 | 12:22 | [9 empty] | A, B, C, D & E - Sewing | 6.6667 | 5 | 7:29 | 8:49
E. Finishing:
I. Sew on the side panels. 120s | [7 empty] | A, B, C, D & E - Sewing | 13.3333 | 5 | 12:27 | 15:07 | [9 empty] | A, B, C, D & E - Sewing | 13.3333 | 5 | 8:54 | 12:04
II. Add ZigZag to the top of the hanging big pocket. 14s | [7 empty] | A - Sewing | 1.5556 | 1 | 15:12 | 16:46 | [9 empty] | A - Sewing | 1.5556 | 1 | 12:09 | 13:42
5. INSPECTION:
﻿﻿﻿Clean and inspect inside. 30s | [14 empty] | F, G & H - Other | 3.3333 | 3 | 7:00 | 8:07 |  |  | F, G & H - Other | 3.3333 | 3 | 13:47 | 14:54
Turn right side out. 50s | [14 empty] | F, G & H - Other | 5.5556 | 3 | 8:12 | 10:03 | [9 empty] | Whole Team | 5.5556 | 8 | 7:00 | 7:42
﻿﻿﻿Insert the foam piece into the headrest. 30s | [14 empty] | F, G & H - Other | 3.3333 | 3 | 10:08 | 11:14 | [9 empty] | Whole Team | 3.3333 | 8 | 7:47 | 8:12
﻿﻿﻿Pack. 60s | [14 empty] | F, G & H - Other | 6.6667 | 3 | 11:19 | 13:33 | [9 empty] | Whole Team | 6.6667 | 8 | 8:17 | 9:07
Non sewing team member - Work done in parallel with prior step