## Prod Plan 0115
|  |  |  | Thursday - 1/15/2025 | [7 empty] | Friday - 1/16/2025 | [7 empty] | Saturday - 1/17/2025
Task ID | FB Task ID | Component | Task | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output
CFA1 | 1 | Fabric | Cut Fabric | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
CTA1 | 2 | Trim | Cut Velcro | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
PSA1 | 3 | Fabric | Sew flag on panel | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SA1 | 4 | A1. Small Velcro Pocket | Hem short edge | 0 |  | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SA2 | 5 | A2. Small Velcro Pocket | Sew hook velcro | 0 |  | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB1 | 6 | B1. Connector Strap | Sew the panel together along the long sides | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB2 | 7 | B2. Connector Strap | Turn inside out | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB3 | 8 | B3. Connector Strap | Sew the 2 long sides of the connector Strap panel | 0 |  | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB4 | 9 | B4. Connector Strap | Sew the connector strap to the small Velcro pocket, add the loop Velcro. | 0 |  | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB5 | 10 | B5. Connector Strap | Close the sides of the small Velcro pocket. | -35 |  | -0.67353 | 2 | 6:35 | 6:45 | -35 | 400 | 0 | Maricela | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SB6 | 11 | B6. Connector Strap | Cut threads, Turn right side out, Cut corners | -28 |  | -0.57035 | 2 | 14:30 | 14:43 | -28 | 400 | 0 | Patty | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SC1 | 12 | C1. Hanging Big Pocket | Hem one short side | 0 |  | 0 | 1 | 6:35 | 7:05 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC2 | 13 | C2. Hanging Big Pocket | Fold to the marking, and close both sides | 0 |  | 0 | 2 | 10:30 | 11:00 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC3 | 14 | C3. Hanging Big Pocket | Add stitching to the lower corners to create volume | 0 |  | 0 | 2 | 6:35 | 7:05 | 0 | 0 | 0 | Oralia S. | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SC4 | 15 | C4. Hanging Big Pocket | Turn right side out | -31 |  | -0.68594 | 2 | 14:20 | 14:29 | -31 | 400 | 0 | Pilar | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SC5 | 16 | C5. Hanging Big Pocket | Add straight single-stitching to the top of the pocket | 0 |  | 0 |  |  |  |  | 0 | 0 | Angelica, Oralia R | 0 | 2 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SC6 | 17 | C6. Hanging Big Pocket | Sew the center stitch | 25 |  | 0.3123 |  |  |  |  | 375 | 25 | All | 0.3123 | 6 | 6:35 | 7:08 | 25 | 400 | 0 |  | 0 |  |  |  |  | 0
SC7 | 18 | C7. Bartack | Add the bartack to the top of the hanging big pocket | 0 |  | 0 |  |  |  |  | 0 | 0 | All | 0 | 6 | 7:13 | 7:43 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SC8 | 19 | C8. Hanging Big Pocket | Stitch the connector strap to the large pocket | 10 |  | 0.11607 |  |  |  |  | 390 | 10 | All | 0.11607 | 6 | 7:48 | 8:19 | 10 | 400 | 0 |  | 0 |  |  |  |  | 0
SD1 | 20 | D1. Cushion Cover | Sew the zipper onto the left panel with USA flag. | 0 |  | 0 | 1 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SD2 | 21 | D2. Cushion Cover | Sew the zipper with hemming foot onto the right panel without the flag | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SD3 | 22 | D3. Cushion Cover | Cut extra material off add the zipper pull | -17 |  | -0.65842 | 1 | 6:00 | 5:50 | -17 | 400 | 0 | Julieta, Obet | 0 | 2 | 6:00 | 6:30 | 0 | 0 | 0 |  | 0 |  |  |  |  | 0
SD4 | 23 | D4. Cushion Cover | Add stitch to both zipper ends | 57 |  | 1.0687 |  |  |  |  | 343 | 57 | Jackie, Maricella | 1.0687 | 2 | 6:00 | 7:02 | 57 | 400 | 0 |  | 0 |  |  |  |  | 0
SD5 | 24 | D5. Cushion Cover | Sew the long sides closed | -93 |  | -2.9085 |  |  |  |  | 493 | -93 | All Sewing | -2.9085 | 6 | 7:07 | 7:08 | -93 | 400 | 0 |  | 0 |  |  |  |  | 0
SD6 | 25 | D6.Cushion Cover | Sew front panel with pockets to zipper panel | -25 |  | -0.33982 |  |  |  |  | 425 | -25 | All Sewing | -0.33982 | 6 | 7:13 | 7:40 | -25 | 400 | 0 |  | 0 |  |  |  |  | 0
SD7 | 26 | D7. Cushion Cover | Sew on the side panels | -50 |  | -2.6611 |  |  |  |  | 450 | -50 | All Sewing | -2.6611 | 6 | 7:45 | 7:48 | -50 | 400 | 0 |  | 0 |  |  |  |  | 0
SD8 | 27 | D8. Cushion Cover | Turn right side out | 202 |  | 7.3775 |  |  |  |  | 198 | 202 | All | 7.3775 | 12 | 7:53 | 9:00 | 202 | 400 | 0 |  | 0 |  |  |  |  | 0
IFA | 28 | A. Inspection Quality | Clean and inspect for any loose threads, missing, flag, ect. | -233 |  | -5.7089 |  |  |  |  | 633 | -233 | All | -5.7089 | 12 | 9:05 | 9:06 | -233 | 400 | 0 |  | 0 |  |  |  |  | 0
IFB | 29 | B. Inspection Insert Foam | Insert foam piece into the headrest. | 164 |  | 3.8435 |  |  |  |  | 236 | 164 |  | 3.8435 | 12 | 9:11 | 10:01 | 164 | 400 | 0 |  | 0 |  |  |  |  | 0
IFC | 30 | C. Inspection Bag | Individually bagged into poly bag S-1997 Size: 9 x 24 | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 | 12 | 10:06 | 10:43 | 208 | 400 | 0 |  | 0 |  |  |  |  | 0
IFD | 31 | D. Inspection Pack | Pack into cartons | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 | 12 | 10:48 | 11:26 | 208 | 400 | 0 |  | 0 |  |  |  |  | 0

## Prod Plan G
|  |  |  | Thursday - 1/15/2025 | [7 empty] | Friday - 1/16/2025 | [7 empty] | Saturday - 1/17/2025
Task ID | FB Task ID | Component | Task | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output | Units to Complete | Names | Hours Required | # of People | Start Time | Finish Time | Day Output | Total Output
CFA1 | 1 | Fabric | Cut Fabric | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
CTA1 | 2 | Trim | Cut Velcro | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
PSA1 | 3 | Fabric | Sew flag on panel | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SA1 | 4 | A1. Small Velcro Pocket | Hem short edge | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SA2 | 5 | A2. Small Velcro Pocket | Sew hook velcro | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB1 | 6 | B1. Connector Strap | Sew the panel together along the long sides | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB2 | 7 | B2. Connector Strap | Turn inside out | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB3 | 8 | B3. Connector Strap | Sew the 2 long sides of the connector Strap panel | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB4 | 9 | B4. Connector Strap | Sew the connector strap to the small Velcro pocket, add the loop Velcro. | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SB5 | 10 | B5. Connector Strap | Close the sides of the small Velcro pocket. | -35 |  | -0.67353 |  |  |  |  | 435 | -35 |  | -0.67353 |  |  |  |  | 435 | -35 |  | -0.67353 |  |  |  |  | 435
SB6 | 11 | B6. Connector Strap | Cut threads, Turn right side out, Cut corners | -28 |  | -0.57035 |  |  |  |  | 428 | -28 |  | -0.57035 |  |  |  |  | 428 | -28 |  | -0.57035 |  |  |  |  | 428
SC1 | 12 | C1. Hanging Big Pocket | Hem one short side | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC2 | 13 | C2. Hanging Big Pocket | Fold to the marking, and close both sides | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC3 | 14 | C3. Hanging Big Pocket | Add stitching to the lower corners to create volume | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC4 | 15 | C4. Hanging Big Pocket | Turn right side out | -31 |  | -0.68594 |  |  |  |  | 431 | -31 |  | -0.68594 |  |  |  |  | 431 | -31 |  | -0.68594 |  |  |  |  | 431
SC5 | 16 | C5. Hanging Big Pocket | Add straight single-stitching to the top of the pocket | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC6 | 17 | C6. Hanging Big Pocket | Sew the center stitch | 25 |  | 0.3123 |  |  |  |  | 375 | 25 |  | 0.3123 |  |  |  |  | 375 | 25 |  | 0.3123 |  |  |  |  | 375
SC7 | 18 | C7. Bartack | Add the bartack to the top of the hanging big pocket | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SC8 | 19 | C8. Hanging Big Pocket | Stitch the connector strap to the large pocket | 10 |  | 0.11607 |  |  |  |  | 390 | 10 |  | 0.11607 |  |  |  |  | 390 | 10 |  | 0.11607 |  |  |  |  | 390
SD1 | 20 | D1. Cushion Cover | Sew the zipper onto the left panel with USA flag. | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SD2 | 21 | D2. Cushion Cover | Sew the zipper with hemming foot onto the right panel without the flag | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0 | 0 |  | 0 |  |  |  |  | 0
SD3 | 22 | D3. Cushion Cover | Cut extra material off add the zipper pull | -17 |  | -0.65842 |  |  |  |  | 417 | -17 |  | -0.65842 |  |  |  |  | 417 | -17 |  | -0.65842 |  |  |  |  | 417
SD4 | 23 | D4. Cushion Cover | Add stitch to both zipper ends | 57 |  | 1.0687 |  |  |  |  | 343 | 57 |  | 1.0687 |  |  |  |  | 343 | 57 |  | 1.0687 |  |  |  |  | 343
SD5 | 24 | D5. Cushion Cover | Sew the long sides closed | -93 |  | -2.9085 |  |  |  |  | 493 | -93 |  | -2.9085 |  |  |  |  | 493 | -93 |  | -2.9085 |  |  |  |  | 493
SD6 | 25 | D6.Cushion Cover | Sew front panel with pockets to zipper panel | -25 |  | -0.33982 |  |  |  |  | 425 | -25 |  | -0.33982 |  |  |  |  | 425 | -25 |  | -0.33982 |  |  |  |  | 425
SD7 | 26 | D7. Cushion Cover | Sew on the side panels | -50 |  | -2.6611 |  |  |  |  | 450 | -50 |  | -2.6611 |  |  |  |  | 450 | -50 |  | -2.6611 |  |  |  |  | 450
SD8 | 27 | D8. Cushion Cover | Turn right side out | 202 |  | 7.3775 |  |  |  |  | 198 | 202 |  | 7.3775 |  |  |  |  | 198 | 202 |  | 7.3775 |  |  |  |  | 198
IFA | 28 | A. Inspection Quality | Clean and inspect for any loose threads, missing, flag, ect. | -233 |  | -5.7089 |  |  |  |  | 633 | -233 |  | -5.7089 |  |  |  |  | 633 | -233 |  | -5.7089 |  |  |  |  | 633
IFB | 29 | B. Inspection Insert Foam | Insert foam piece into the headrest. | 164 |  | 3.8435 |  |  |  |  | 236 | 164 |  | 3.8435 |  |  |  |  | 236 | 164 |  | 3.8435 |  |  |  |  | 236
IFC | 30 | C. Inspection Bag | Individually bagged into poly bag S-1997 Size: 9 x 24 | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 |  |  |  |  | 192
IFD | 31 | D. Inspection Pack | Pack into cartons | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 |  |  |  |  | 192 | 208 |  | 1.5455 |  |  |  |  | 192

## Analysis
[20 empty] | TOTAL |  |  |  |  | 2.772 | 1.6024
Average of Rate/Hour | Column Labels
Row Labels | 00-Prod Dev | Angelica | Cindy | Fransico | Jackie | Julieta | Maricela | Noe | Oralia R | Oralia S | Patty | Pilar | Grand Total | Min | Max | Avg | Min/Dev | Max/Dev | Avg/Dev | Task ID | Dev Avg (pcs/hr) | Actual Avg (pcs/hr) | Balance | Check | Hours Dev | Hours Actual
CFA1 | 40 | [11 empty] | 40 | 0 | 0 | #DIV/0! | 0% | 0% | #DIV/0! | CFA1 | 40 | 40 | 0 | CFA1 | 0 | 0
CTA1 | 1800 | [11 empty] | 1800 | 0 | 0 | #DIV/0! | 0% | 0% | #DIV/0! | CTA1 | 1800 | 1800 | 0 | CTA1 | 0 | 0
IFA | 120 | 35 | 30 | 23.1373 |  |  | 82 | 18.1805 | 67.5 |  | 25.8929 | 44.8 | 39.327 | 18.1805 | 82 | 40.8138 | 15.15% | 68.33% | 34.01% | IFA | 39.327 | 40.8138 | -233 | IFA | -5.9247 | -5.7089
IFB | 72 | [9 empty] | 31.5824 | 53.7568 | 50.4936 | 31.5824 | 53.7568 | 42.6696 | 43.86% | 74.66% | 59.26% | IFB | 50.4936 | 42.6696 | 164 | IFB | 3.2479 | 3.8435
IFC | 120 |  |  |  |  | 134.5882 | [6 empty] | 129.7255 | 134.5882 | 134.5882 | 134.5882 | 112.2% | 112.2% | 112.2% | IFC | 129.7255 | 134.5882 | 208 | IFC | 1.6034 | 1.5455
IFD | 60 |  |  |  |  | 134.5882 | [6 empty] | 109.7255 | 134.5882 | 134.5882 | 134.5882 | 224.3% | 224.3% | 224.3% | IFD | 109.7255 | 134.5882 | 208 | IFD | 1.8956 | 1.5455
PSA1 | 514.2857 |  | 304.3478 | [9 empty] | 374.3271 | 304.3478 | 304.3478 | 304.3478 | 59.18% | 59.18% | 59.18% | PSA1 | 374.3271 | 304.3478 | 0 | PSA1 | 0 | 0
SA1 | 180 | 94.1176 |  |  | 50 |  |  |  | 48 |  |  |  | 93.0294 | 48 | 94.1176 | 64.0392 | 26.67% | 52.29% | 35.58% | SA1 | 93.0294 | 64.0392 | 0 | SA1 | 0 | 0
SA2 | 144 |  |  |  | 39.375 | 16.5 | 71.4286 | [5 empty] | 62.1357 | 16.5 | 71.4286 | 42.4345 | 11.46% | 49.6% | 29.47% | SA2 | 62.1357 | 42.4345 | 0 | SA2 | 0 | 0
SB1 | 300 | [5 empty] | 150 |  | 72 | 168 |  |  | 172.5 | 72 | 168 | 130 | 24% | 56% | 43.33% | SB1 | 172.5 | 130 | 0 | SB1 | 0 | 0
SB2 | 60 |  |  | 48.6795 |  |  |  | 48.6795 |  |  | 46.2308 |  | 49.5971 | 46.2308 | 48.6795 | 47.8632 | 77.05% | 81.13% | 79.77% | SB2 | 49.5971 | 47.8632 | 0 | SB2 | 0 | 0
SB3 | 144 |  | 36.4615 |  |  |  | 64.5333 |  |  | 71.0769 |  |  | 77.4297 | 36.4615 | 71.0769 | 57.3573 | 25.32% | 49.36% | 39.83% | SB3 | 77.4297 | 57.3573 | 0 | SB3 | 0 | 0
SB4 | 102.8571 |  |  |  | 50.1349 | 49.7143 | 54.9426 | [5 empty] | 58.4755 | 49.7143 | 54.9426 | 51.5973 | 48.33% | 53.42% | 50.16% | SB4 | 58.4755 | 51.5973 | 0 | SB4 | 0 | 0
SB5 | 240 |  | 60 |  | 50.9431 | 30 | 66.9167 | [5 empty] | 75.9533 | 30 | 66.9167 | 51.9649 | 12.5% | 27.88% | 21.65% | SB5 | 75.9533 | 51.9649 | -35 | SB5 | -0.46081 | -0.67353
SB6 | 144 |  |  |  | 44.4444 | [5 empty] | 51.2105 | 51.6223 | 62.1694 | 44.4444 | 51.6223 | 49.0924 | 30.86% | 35.85% | 34.09% | SB6 | 62.1694 | 49.0924 | -28 | SB6 | -0.45038 | -0.57035
SC1 | 211.7647 | 156.9231 | [6 empty] | 72.6316 | 109.0909 |  |  | 137.6026 | 72.6316 | 156.9231 | 112.8819 | 34.3% | 74.1% | 53.31% | SC1 | 137.6026 | 112.8819 | 0 | SC1 | 0 | 0
SC2 | 102.8571 | 70.4211 | [6 empty] | 70.8 | 72.7273 |  |  | 79.2014 | 70.4211 | 72.7273 | 71.3161 | 68.46% | 70.71% | 69.34% | SC2 | 79.2014 | 71.3161 | 0 | SC2 | 0 | 0
SC3 | 100 | 78.7059 |  |  | 126.9231 |  |  |  | 68.2902 |  |  |  | 85.0833 | 68.2902 | 126.9231 | 91.3064 | 68.29% | 126.9% | 91.31% | SC3 | 85.0833 | 91.3064 | 0 | SC3 | 0 | 0
SC4 | 144 |  |  | 24.1471 |  |  |  | 52.4971 |  |  | 37.4095 | 66.72 | 52.8392 | 24.1471 | 66.72 | 45.1934 | 16.77% | 46.33% | 31.38% | SC4 | 52.8392 | 45.1934 | -31 | SC4 | -0.58669 | -0.68594
SC5 | 240 | 82.6772 | [6 empty] | 69 | 71.875 |  |  | 107.0854 | 69 | 82.6772 | 74.5174 | 28.75% | 34.45% | 31.05% | SC5 | 107.0854 | 74.5174 | 0 | SC5 | 0 | 0
SC6 | 180 | 60 |  |  | 95.0588 |  | 108 |  | 57.1429 |  |  |  | 99.2101 | 57.1429 | 108 | 80.0504 | 31.75% | 60% | 44.47% | SC6 | 99.2101 | 80.0504 | 25 | SC6 | 0.25199 | 0.3123
SC7 | 257.1429 |  | 70.2857 | [5 empty] | 150.0508 |  |  |  | 155.5162 | 70.2857 | 150.0508 | 110.1683 | 27.33% | 58.35% | 42.84% | SC7 | 155.5162 | 110.1683 | 0 | SC7 | 0 | 0
SC8 | 400 | 58.2524 |  |  | 97.8261 |  | 102.3953 | [5 empty] | 143.8774 | 58.2524 | 102.3953 | 86.1579 | 14.56% | 25.6% | 21.54% | SC8 | 143.8774 | 86.1579 | 10 | SC8 | 0.069504 | 0.11607
SD1 | 36 |  | 41.9207 | [9 empty] | 40.4405 | 41.9207 | 41.9207 | 41.9207 | 116.4% | 116.4% | 116.4% | SD1 | 40.4405 | 41.9207 | 0 | SD1 | 0 | 0
SD2 | 120 |  | 76.6734 | [9 empty] | 91.1156 | 76.6734 | 76.6734 | 76.6734 | 63.89% | 63.89% | 63.89% | SD2 | 91.1156 | 76.6734 | 0 | SD2 | 0 | 0
SD3 | 200 |  |  |  |  | 22.1159 |  |  | 29.5228 |  |  |  | 51.7604 | 22.1159 | 29.5228 | 25.8194 | 11.06% | 14.76% | 12.91% | SD3 | 51.7604 | 25.8194 | -17 | SD3 | -0.32844 | -0.65842
SD4 | 60 |  | 40.3009 |  |  |  | 66.375 | [5 empty] | 46.0226 | 40.3009 | 66.375 | 53.338 | 67.17% | 110.6% | 88.9% | SD4 | 46.0226 | 53.338 | 57 | SD4 | 1.2385 | 1.0687
SD5 | 120 | 17.575 | 35.2634 | [6 empty] | 43.0882 |  |  | 38.7466 | 17.575 | 43.0882 | 31.9755 | 14.65% | 35.91% | 26.65% | SD5 | 38.7466 | 31.9755 | -93 | SD5 | -2.4002 | -2.9085
SD6 | 120 |  |  |  | 46.7143 |  |  |  |  | 100.4203 |  |  | 85.7816 | 46.7143 | 100.4203 | 73.5673 | 38.93% | 83.68% | 61.31% | SD6 | 85.7816 | 73.5673 | -25 | SD6 | -0.29144 | -0.33982
SD7 | 120 | 21.6628 | 12 |  | 11 |  | 19.619 |  | 8.4545 | 40 |  |  | 25.6402 | 8.4545 | 40 | 18.7894 | 7.045% | 33.33% | 15.66% | SD7 | 25.6402 | 18.7894 | -50 | SD7 | -1.9501 | -2.6611
SD8 | 120 |  |  | 12.3283 |  |  | 70 |  | 9 |  | 19.861 | 25.7143 | 29.4559 | 9 | 70 | 27.3807 | 7.5% | 58.33% | 22.82% | SD8 | 29.4559 | 27.3807 | 202 | SD8 | 6.8577 | 7.3775
Grand Total | 212.0293 | 49.5655 | 67.2459 | 24.1241 | 53.5644 | 75.4221 | 70.7346 | 38.0069 | 65.6654 | 76.6224 | 32.5465 | 49.2063 | 79.8722
Product | (Multiple Items) |  | Order Quantity |  | 400
Row Labels | Sum of Completed Units |  | Task ID | Completed Units | Balance
CFA1 | 400 |  | CFA1 | 400 | 0
CTA1 | 400 |  | CTA1 | 400 | 0
IFA | 633 |  | IFA | 633 | -233
IFB | 236 |  | IFB | 236 | 164
IFC | 192 |  | IFC | 192 | 208
IFD | 192 |  | IFD | 192 | 208
PSA1 | 400 |  | PSA1 | 400 | 0
SA1 | 400 |  | SA1 | 400 | 0
SA2 | 400 |  | SA2 | 400 | 0
SB1 | 400 |  | SB1 | 400 | 0
SB2 | 400 |  | SB2 | 400 | 0
SB3 | 400 |  | SB3 | 400 | 0
SB4 | 400 |  | SB4 | 400 | 0
SB5 | 435 |  | SB5 | 435 | -35
SB6 | 428 |  | SB6 | 428 | -28
SC1 | 400 |  | SC1 | 400 | 0
SC2 | 400 |  | SC2 | 400 | 0
SC3 | 400 |  | SC3 | 400 | 0
SC4 | 431 |  | SC4 | 431 | -31
SC5 | 400 |  | SC5 | 400 | 0
SC6 | 375 |  | SC6 | 375 | 25
SC7 | 400 |  | SC7 | 400 | 0
SC8 | 390 |  | SC8 | 390 | 10
SD1 | 400 |  | SD1 | 400 | 0
SD2 | 400 |  | SD2 | 400 | 0
SD3 | 417 |  | SD3 | 417 | -17
SD4 | 343 |  | SD4 | 343 | 57
SD5 | 493 |  | SD5 | 493 | -93
SD6 | 425 |  | SD6 | 425 | -25
SD7 | 450 |  | SD7 | 450 | -50
SD8 | 198 |  | SD8 | 198 | 202
Grand Total | 12038

## Production Data
Product | Date | Name | Task ID | FB Task # | Component | Start Time | Finish Time | Completed Units | Elapse Time | Sew Time | Rate/Hour
Tenjam | 2026-01-01 | 00-Prod Dev | CFA1 | 1 | Fabric |  |  | 400 |  |  | 40
Tenjam | 2026-01-01 | 00-Prod Dev | CTA1 | 2 | Trim |  |  | 400 |  |  | 1800
Tenjam | 2026-01-01 | 00-Prod Dev | IFA | 28 | A. Inspection Quality | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | IFB | 29 | B. Inspection Insert Foam | [5 empty] | 72
Tenjam | 2026-01-01 | 00-Prod Dev | IFC | 30 | C. Inspection Bag | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | IFD | 31 | D. Inspection Pack | [5 empty] | 60
Tenjam | 2026-01-01 | 00-Prod Dev | PSA1 | 3 | Fabric | [5 empty] | 514.2857
Tenjam | 2026-01-01 | 00-Prod Dev | SA1 | 4 | A1. Small Velcro Pocket | [5 empty] | 180
Tenjam | 2026-01-01 | 00-Prod Dev | SA2 | 5 | A2. Small Velcro Pocket | [5 empty] | 144
Tenjam | 2026-01-01 | 00-Prod Dev | SB1 | 6 | B1. Connector Strap | [5 empty] | 300
Tenjam | 2026-01-01 | 00-Prod Dev | SB2 | 7 | B2. Connector Strap | [5 empty] | 60
Tenjam | 2026-01-01 | 00-Prod Dev | SB3 | 8 | B3. Connector Strap | [5 empty] | 144
Tenjam | 2026-01-01 | 00-Prod Dev | SB4 | 9 | B4. Connector Strap | [5 empty] | 102.8571
Tenjam | 2026-01-01 | 00-Prod Dev | SB5 | 10 | B5. Connector Strap | [5 empty] | 240
Tenjam | 2026-01-01 | 00-Prod Dev | SB6 | 11 | B6. Connector Strap | [5 empty] | 144
Tenjam | 2026-01-01 | 00-Prod Dev | SC1 | 12 | C1. Hanging Big Pocket | [5 empty] | 211.7647
Tenjam | 2026-01-01 | 00-Prod Dev | SC2 | 13 | C2. Hanging Big Pocket | [5 empty] | 102.8571
Tenjam | 2026-01-01 | 00-Prod Dev | SC3 | 14 | C3. Hanging Big Pocket | [5 empty] | 100
Tenjam | 2026-01-01 | 00-Prod Dev | SC4 | 15 | C4. Hanging Big Pocket | [5 empty] | 144
Tenjam | 2026-01-01 | 00-Prod Dev | SC5 | 16 | C5. Hanging Big Pocket | [5 empty] | 240
Tenjam | 2026-01-01 | 00-Prod Dev | SC6 | 17 | C6. Hanging Big Pocket | [5 empty] | 180
Tenjam | 2026-01-01 | 00-Prod Dev | SC7 | 18 | C7. Bartack | [5 empty] | 257.1429
Tenjam | 2026-01-01 | 00-Prod Dev | SC8 | 19 | C8. Hanging Big Pocket | [5 empty] | 400
Tenjam | 2026-01-01 | 00-Prod Dev | SD1 | 20 | D1. Cushion Cover | [5 empty] | 36
Tenjam | 2026-01-01 | 00-Prod Dev | SD2 | 21 | D2. Cushion Cover | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | SD3 | 22 | D3. Cushion Cover | [5 empty] | 200
Tenjam | 2026-01-01 | 00-Prod Dev | SD4 | 23 | D4. Cushion Cover | [5 empty] | 60
Tenjam | 2026-01-01 | 00-Prod Dev | SD5 | 24 | D5. Cushion Cover | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | SD6 | 25 | D6.Cushion Cover | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | SD7 | 26 | D7. Cushion Cover | [5 empty] | 120
Tenjam | 2026-01-01 | 00-Prod Dev | SD8 | 27 | D8. Cushion Cover | [5 empty] | 120
Tenjam - Blue | 2026-01-12 | Angelica | SA1 |  | A1 | 8:30 | 13:15 | 400 | 4.75 | 4.25 | 94.1176
Tenjam - Blue | 2026-01-12 | Angelica | SC1 |  | C1 | 13:15 | 14:20 | 170 | 1.0833 | 1.0833 | 156.9231
Tenjam - Blue | 2026-01-12 | Angelica | SC2 |  | C2 | 14:20 | 17:30 | 223 | 3.1667 | 3.1667 | 70.4211
Tenjam - Blue | 2026-01-12 | Cindy | PSA1 |  | A1 | 9:30 | 10:30 | 400 | 1 | 1 | 400
Tenjam - Blue | 2026-01-12 | Cindy | SB3 |  | B3 | 10:40 | 15:30 | 158 | 4.8333 | 4.3333 | 36.4615
Tenjam - Blue | 2026-01-12 | Cindy | SD2 |  | D2 | 15:35 | 17:00 | 100 | 1.4167 | 1.4167 | 70.5882
Tenjam - Blue | 2026-01-12 | Fransico | SB2 |  | B2 | 9:45 | 14:35 | 133 | 4.8333 | 4.3333 | 30.6923
Tenjam - Blue | 2026-01-12 | Jackie | SB4 |  | B4 | 4:45 | 5:30 | 22 | 0.75 | 0.75 | 29.3333
Tenjam - Blue | 2026-01-12 | Jackie | SA2 |  | A2 | 10:30 | 16:45 | 345 | 6.25 | 5.75 | 60
Tenjam - Blue | 2026-01-12 | Julieta | SA2 |  | A2 | 13:40 | 17:00 | 55 | 3.3333 | 3.3333 | 16.5
Tenjam - Blue | 2026-01-12 | Julieta | SB5 |  | B5 | 17:00 | 17:30 | 15 | 0.5 | 0.5 | 30
Tenjam - Blue | 2026-01-12 | Maricela | SB1 |  | B1 | 8:30 | 11:10 | 400 | 2.6667 | 2.6667 | 150
Tenjam - Blue | 2026-01-12 | Maricela | SB3 |  | B3 | 11:35 | 15:20 | 242 | 3.75 | 3.75 | 64.5333
Tenjam - Blue | 2026-01-12 | Maricela | SB4 |  | B4 | 15:20 | 16:50 | 55 | 1.5 | 1.5 | 36.6667
Tenjam - Blue | 2026-01-12 | Noe | SB2 |  | B2 | 9:45 | 14:35 | 133 | 4.8333 | 4.3333 | 30.6923
Tenjam - Blue | 2026-01-12 | Oralia R | SC1 |  | C1 | 11:35 | 14:45 | 230 | 3.1667 | 3.1667 | 72.6316
Tenjam - Blue | 2026-01-12 | Oralia R | SC2 |  | C2 | 15:00 | 17:30 | 177 | 2.5 | 2.5 | 70.8
Tenjam - Blue | 2026-01-12 | Patty | SB2 |  | B2 | 9:45 | 14:35 | 134 | 4.8333 | 4.3333 | 30.9231
Tenjam - Blue | 2026-01-13 | Angelica | SC3 |  | C3 | 6:00 | 8:50 | 223 | 2.8333 | 2.8333 | 78.7059
Tenjam - Blue | 2026-01-13 | Angelica | SC6 |  | C6 | 8:50 | 12:40 | 200 | 3.8333 | 3.3333 | 60
Tenjam - Blue | 2026-01-13 | Angelica | SC5 |  | C5 | 12:40 | 14:47 | 175 | 2.1167 | 2.1167 | 82.6772
Tenjam - Blue | 2026-01-13 | Angelica | SC8 |  | C8 | 14:47 | 16:30 | 100 | 1.7167 | 1.7167 | 58.2524
Tenjam - Blue | 2026-01-13 | Cindy | SD1 |  | D1 | 6:00 | 14:35 | 300 | 8.5833 | 8.0833 | 37.1134
Tenjam - Blue | 2026-01-13 | Cindy | SC7 |  | C7 | 14:45 | 16:30 | 123 | 1.75 | 1.75 | 70.2857
Tenjam - Blue | 2026-01-13 | Jackie | SB5 |  | B5 | 6:00 | 9:25 | 160 | 3.4167 | 3.4167 | 46.8293
Tenjam - Blue | 2026-01-13 | Jackie | SB4 |  | B4 | 9:30 | 11:45 | 120 | 2.25 | 1.75 | 68.5714
Tenjam - Blue | 2026-01-13 | Jackie | SB6 |  | B6 | 11:45 | 14:00 | 100 | 2.25 | 2.25 | 44.4444
Tenjam - Blue | 2026-01-13 | Jackie | SC3 |  | C3 | 14:00 | 14:52 | 110 | 0.86667 | 0.86667 | 126.9231
Tenjam - Blue | 2026-01-13 | Jackie | SC8 |  | C8 | 15:44 | 16:30 | 75 | 0.76667 | 0.76667 | 97.8261
Tenjam - Blue | 2026-01-13 | Julieta | SB4 |  | B4 | 6:00 | 8:20 | 116 | 2.3333 | 2.3333 | 49.7143
Tenjam - Blue | 2026-01-13 | Julieta | SD3 |  | D3 | 8:20 | 16:30 | 196 | 8.1667 | 7.6667 | 25.5652
Tenjam - Blue | 2026-01-13 | Maricela | SB5 |  | B5 | 6:00 | 9:00 | 192 | 3 | 3 | 64
Tenjam - Blue | 2026-01-13 | Maricela | SB4 |  | B4 | 9:00 | 11:50 | 165 | 2.8333 | 2.3333 | 70.7143
Tenjam - Blue | 2026-01-13 | Maricela | SD4 |  | D4 | 11:50 | 14:30 | 177 | 2.6667 | 2.6667 | 66.375
Tenjam - Blue | 2026-01-13 | Maricela | SC8 |  | C8 | 14:40 | 16:30 | 160 | 1.8333 | 1.8333 | 87.2727
Tenjam - Blue | 2026-01-13 | Oralia R | SC3 |  | C3 | 6:00 | 8:50 | 177 | 2.8333 | 2.8333 | 62.4706
Tenjam - Blue | 2026-01-13 | Oralia R | SC6 |  | C6 | 9:00 | 13:00 | 200 | 4 | 3.5 | 57.1429
Tenjam - Blue | 2026-01-13 | Oralia R | SC5 |  | C5 | 13:00 | 14:40 | 115 | 1.6667 | 1.6667 | 69
Tenjam - Blue | 2026-01-13 | Oralia R | SC7 |  | C7 | 14:45 | 16:30 | 235 | 1.75 | 1.75 | 134.2857
Tenjam - Blue | 2026-01-13 | Patty | SB6 |  | B6 | 12:30 | 15:30 | 150 | 3 | 3 | 50
Tenjam - Blue | 2026-01-13 | Pilar | SC4 |  | C4 | 7:50 | 12:30 | 278 | 4.6667 | 4.1667 | 66.72
Tenjam - Blue | 2026-01-13 | Pilar | SB6 |  | B6 | 12:30 | 15:30 | 150 | 3 | 3 | 50
Tenjam - White | 2026-01-14 | Cindy | SD1 | 20 | D1 | 2:00 | 4:30 | 100 | 2.5 | 2.5 | 40
Tenjam - White | 2026-01-14 | Cindy | PSA1 | 3 | Prep | 6:35 | 8:30 | 400 | 1.9167 | 1.9167 | 208.6957
Tenjam - White | 2026-01-14 | Cindy | SD2 | 21 | D2 | 8:40 | 14:00 | 400 | 5.3333 | 4.8333 | 82.7586
Tenjam - White | 2026-01-14 | Fransico | SB2 | 7 | B2 | 7:45 | 9:15 | 100 | 1.5 | 1.5 | 66.6667
Tenjam - White | 2026-01-14 | Noe | SB2 | 7 | B2 | 7:45 | 9:15 | 100 | 1.5 | 1.5 | 66.6667
Tenjam - White | 2026-01-14 | Oralia R | SB1 | 6 | B1 | 7:15 | 7:45 | 36 | 0.5 | 0.5 | 72
Tenjam - White | 2026-01-14 | Oralia R | SA1 | 4 | A1 | 12:10 | 16:20 | 200 | 4.1667 | 4.1667 | 48
Tenjam - White | 2026-01-14 | Oralia S | SB1 | 6 | B1 | 6:00 | 8:10 | 364 | 2.1667 | 2.1667 | 168
Tenjam - White | 2026-01-14 | Oralia S | SB3 | 8 | B3 | 12:10 | 16:30 | 382 | 4.3333 | 4.3333 | 88.1538
Tenjam - White | 2026-01-14 | Patty | SB2 | 7 | B2 | 7:45 | 11:00 | 200 | 3.25 | 3.25 | 61.5385
Tenjam - White | 2026-01-15 | Oralia R | SD3 | 22 | D3 | 6:00 | 10:40 | 189 | 4.6667 | 4.6667 | 40.5 | 11:40-12:10 Lunch
Tenjam - White | 2026-01-15 | Oralia R | SC3 | 14 | C3 | 10:50 | 16:20 | 322 | 5.5 | 5 | 64.4
Tenjam - White | 2026-01-15 | Cindy | SD1 | 20 | D1 | 6:00 | 12:40 | 300 | 6.6667 | 6.1667 | 48.6486
Tenjam - White | 2026-01-15 | Cindy | SD4 | 23 | D4 | 12:45 | 14:15 | 75 | 1.5 | 1.5 | 50
Tenjam - White | 2026-01-15 | Cindy | SB5 | 10 | B5 | 14:15 | 15:55 | 100 | 1.6667 | 1.6667 | 60
Tenjam - White | 2026-01-15 | Cindy | SD4 | 23 | D4 | 15:55 | 16:30 | 30 | 0.58333 | 0.58333 | 51.4286
Tenjam - White | 2026-01-15 | Oralia S | SB3 | 8 | B3 | 6:00 | 6:20 | 18 | 0.33333 | 0.33333 | 54
Tenjam - White | 2026-01-15 | Oralia S | SC1 | 12 | C1 | 6:20 | 10:00 | 400 | 3.6667 | 3.6667 | 109.0909 | Negative 30 Minutes Meeting
Tenjam - White | 2026-01-15 | Oralia S | SC2 | 13 | C2 | 10:00 | 16:00 | 400 | 6 | 5.5 | 72.7273
Tenjam - White | 2026-01-15 | Oralia S | SC5 | 16 | C5 | 16:00 | 16:30 | 25 | 0.5 | 0.5 | 50
Tenjam - White | 2026-01-15 | Jackie | SA1 | 4 | A1 | 6:00 | 10:00 | 200 | 4 | 4 | 50
Tenjam - White | 2026-01-15 | Jackie | SA2 | 5 | A2 | 10:00 | 11:50 | 25 | 1.8333 | 1.3333 | 18.75
Tenjam - White | 2026-01-15 | Jackie | SB4 | 9 | B4 | 12:10 | 15:30 | 175 | 3.3333 | 3.3333 | 52.5
Tenjam - White | 2026-01-15 | Jackie | SB5 | 10 | B5 | 15:30 | 16:30 | 40 | 1 | 1 | 40
Tenjam - White | 2026-01-15 | Maricela | SA2 | 5 | A2 | 6:00 | 11:15 | 375 | 5.25 | 5.25 | 71.4286
Tenjam - White | 2026-01-15 | Maricela | SB4 | 9 | B4 | 11:15 | 15:10 | 225 | 3.9167 | 3.9167 | 57.4468
Tenjam - White | 2026-01-15 | Maricela | SB5 | 10 | B5 | 15:10 | 16:30 | 67 | 1.3333 | 1.3333 | 50.25
Tenjam - White | 2026-01-15 | Patty | SC4 | 15 | C4 | 11:25 | 16:30 | 154 | 5.0833 | 5.0833 | 30.2951
Tenjam - White | 2026-01-15 | Pilar | SB6 | 11 | B6 | 14:56 | 16:30 | 65 | 1.5667 | 1.5667 | 41.4894
Tenjam - White | 2026-01-15 | Julieta | SD3 | 22 | D3 | 10:45 | 16:30 | 98 | 5.75 | 5.25 | 18.6667
Tenjam - Blue | 2026-01-15 | Angelica | SD5 | 23 | D5 | 6:00 | 16:30 | 143 | 10.5 | 10 | 14.3
Tenjam - Blue | 2026-01-16 | Noe | IFA | 28 | A | 7:00 | 8:35 | 31 | 1.5833 | 1.5833 | 19.5789
Tenjam - White | 2026-01-16 | Noe | SC4 | 15 | C4 | 8:50 | 9:00 | 13 | 0.16667 | 0.16667 | 78
Tenjam - White | 2026-01-16 | Noe | SC4 | 15 | C4 | 9:00 | 9:38 | 28 | 0.63333 | 0.63333 | 44.2105
Tenjam - Blue | 2026-01-16 | Noe | IFA | 28 | A | 9:40 | 11:00 | 24 | 1.3333 | 1.3333 | 18
Tenjam - White | 2026-01-16 | Noe | SC4 | 15 | C4 | 11:35 | 12:02 | 22 | 0.45 | 0.45 | 48.8889
Tenjam - Blue | 2026-01-16 | Noe | IFA | 28 | A | 12:05 | 12:33 | 8 | 0.46667 | 0.46667 | 17.1429
Tenjam - White | 2026-01-16 | Noe | SC4 | 15 | C4 | 12:36 | 13:30 | 35 | 0.9 | 0.9 | 38.8889
Tenjam - White | 2026-01-16 | Noe | IFA | 28 | A | 13:40 | 15:20 | 30 | 1.6667 | 1.6667 | 18
Tenjam - White | 2026-01-16 | Oralia S | SC5 | 16 | C5 | 6:00 | 10:00 | 375 | 4 | 4 | 93.75
Tenjam - White | 2026-01-16 | Oralia S | SD6 | 25 | D6 | 10:00 | 11:00 | 55 | 1 | 1 | 55
Tenjam - White | 2026-01-16 | Oralia S | SD6 | 25 | D6 | 11:35 | 13:30 | 150 | 1.9167 | 1.9167 | 78.2609
Tenjam - White | 2026-01-16 | Oralia S | SD6 | 25 | D6 | 13:40 | 13:50 | 28 | 0.16667 | 0.16667 | 168
Tenjam - White | 2026-01-16 | Oralia S | SD5 | 24 | D5 | 13:50 | 15:30 | 50 | 1.6667 | 1.6667 | 30
Tenjam - White | 2026-01-16 | Oralia S | SD5 | 24 | D5 | 15:30 | 16:30 | 50 | 1 | 1 | 50
Tenjam - White | 2026-01-16 | Pilar | SB6 | 11 | B6 | 6:00 | 9:00 | 150 | 3 | 3 | 50
Tenjam - White | 2026-01-16 | Pilar | SB6 | 11 | B6 | 9:00 | 11:00 | 130 | 2 | 2 | 65
Tenjam - Blue | 2026-01-16 | Pilar | IFA | 28 | A | 11:35 | 13:40 | 60 | 2.0833 | 2.0833 | 28.8
Tenjam - Blue | 2026-01-16 | Pilar | IFA | 28 | A | 13:40 | 14:40 | 34 | 1 | 1 | 34
Tenjam - Blue | 2026-01-16 | Pilar | IFB | 29 | B | 14:40 | 14:50 | 12 | 0.16667 | 0.16667 | 72
Tenjam - White | 2026-01-16 | Pilar | IFA | 28 | A | 14:50 | 15:20 | 17 | 0.5 | 0.5 | 34
Tenjam - White | 2026-01-16 | Pilar | IFB | 29 | B | 15:20 | 15:50 | 15 | 0.5 | 0.5 | 30
Tenjam - White | 2026-01-16 | Pilar | SD8 | 27 | D8 | 15:50 | 16:25 | 15 | 0.58333 | 0.58333 | 25.7143
Tenjam - Blue | 2026-01-16 | Fransico | SD8 | 27 | D8 | 7:00 | 8:30 | 27 | 1.5 | 1.5 | 18
Tenjam - White | 2026-01-16 | Fransico | SC4 | 15 | C4 | 8:30 | 9:38 | 23 | 1.1333 | 1.1333 | 20.2941
Tenjam - Blue | 2026-01-16 | Fransico | SD8 | 27 | D8 | 9:41 | 10:50 | 16 | 1.15 | 1.15 | 13.913
Tenjam - Blue | 2026-01-16 | Fransico | SD8 | 28 | D8 | 11:40 | 12:30 | 7 | 0.83333 | 0.83333 | 8.4
Tenjam - White | 2026-01-16 | Fransico | SC4 | 15 | C4 | 12:30 | 13:30 | 28 | 1 | 1 | 28
Tenjam - White | 2026-01-16 | Fransico | SD8 | 28 | D8 | 13:40 | 15:20 | 15 | 1.6667 | 1.6667 | 9
Tenjam - White | 2026-01-16 | Maricela | SB5 | 10 | B5 | 6:00 | 8:00 | 173 | 2 | 2 | 86.5
Tenjam - White | 2026-01-16 | Maricela | SC6 | 17 | C6 | 8:00 | 9:20 | 144 | 1.3333 | 1.3333 | 108
Tenjam - White | 2026-01-16 | Maricela | SC8 | 18 | C8 | 9:20 | 11:00 | 210 | 1.6667 | 1.6667 | 126
Tenjam - White | 2026-01-16 | Maricela | SC8 | 18 | C8 | 11:35 | 13:30 | 180 | 1.9167 | 1.9167 | 93.913
Tenjam - White | 2026-01-16 | Maricela | SD7 | 26 | D7 | 13:40 | 15:20 | 30 | 1.6667 | 1.6667 | 18
Tenjam - White | 2026-01-16 | Maricela | SD7 | 26 | D7 | 15:20 | 16:30 | 22 | 1.1667 | 1.1667 | 18.8571
Tenjam - Blue | 2026-01-16 | Angelica | SD5 | 23 | D5 | 6:00 | 9:00 | 42 | 3 | 3 | 14
Tenjam - Blue | 2026-01-16 | Angelica | SD5 | 23 | D5 | 9:00 | 11:00 | 36 | 2 | 2 | 18
Tenjam - Blue | 2026-01-16 | Angelica | SD5 | 23 | D5 | 11:35 | 12:00 | 10 | 0.41667 | 0.41667 | 24
Tenjam - White | 2026-01-16 | Angelica | SD7 | 26 | D7 | 14:40 | 15:20 | 13 | 0.66667 | 0.66667 | 19.5
Tenjam - White | 2026-01-16 | Angelica | SD7 | 26 | D7 | 15:20 | 16:30 | 22 | 1.1667 | 1.1667 | 18.8571
Tenjam - White | 2026-01-16 | Patty | SC4 | 15 | C4 | 6:00 | 9:00 | 109 | 3 | 3 | 36.3333
Tenjam - White | 2026-01-16 | Patty | SC4 | 15 | C4 | 9:00 | 9:25 | 19 | 0.41667 | 0.41667 | 45.6
Tenjam - White | 2026-01-16 | Patty | SB6 | 11 | B6 | 9:25 | 11:00 | 83 | 1.5833 | 1.5833 | 52.4211
Tenjam - White | 2026-01-16 | Patty | IFA | 29 | A | 11:35 | 12:35 | 35 | 1 | 1 | 35
Tenjam - White | 2026-01-16 | Patty | IFB | 29 | B | 12:35 | 13:40 | 35 | 1.0833 | 1.0833 | 32.3077
Tenjam - White | 2026-01-16 | Patty | IFA | 29 | A | 13:40 | 14:15 | 18 | 0.58333 | 0.58333 | 30.8571
Tenjam - White | 2026-01-16 | Patty | IFB | 29 | B | 14:15 | 14:50 | 18 | 0.58333 | 0.58333 | 30.8571
Tenjam - White | 2026-01-16 | Patty | SD8 | 27 | D8 | 14:50 | 15:05 | 6 | 0.25 | 0.25 | 24
Tenjam - White | 2026-01-16 | Patty | IFA | 28 | A | 15:05 | 15:20 | 6 | 0.25 | 0.25 | 24
Tenjam - White | 2026-01-16 | Patty | SD8 | 27 | D8 | 15:20 | 15:50 | 8 | 0.5 | 0.5 | 16
Tenjam - White | 2026-01-16 | Patty | IFA | 28 | A | 15:50 | 16:25 | 8 | 0.58333 | 0.58333 | 13.7143
Tenjam - White | 2026-01-16 | Jackie | SB5 | 10 | B5 | 7:00 | 7:50 | 55 | 0.83333 | 0.83333 | 66
Tenjam - White | 2026-01-16 | Jackie | SC6 | 17 | C6 | 7:50 | 8:50 | 92 | 1 | 1 | 92
Tenjam - White | 2026-01-16 | Jackie | SC6 | 17 | C6 | 9:00 | 10:25 | 139 | 1.4167 | 1.4167 | 98.1176
Tenjam - White | 2026-01-16 | Jackie | SD6 | 25 | D6 | 10:25 | 11:00 | 16 | 0.58333 | 0.58333 | 27.4286
Tenjam - White | 2026-01-16 | Jackie | SD6 | 25 | D6 | 11:40 | 14:20 | 176 | 2.6667 | 2.6667 | 66
Tenjam - White | 2026-01-16 | Jackie | SD7 | 26 | D7 | 14:20 | 15:20 | 8 | 1 | 1 | 8
Tenjam - White | 2026-01-16 | Jackie | SD7 | 26 | D7 | 15:30 | 16:30 | 12 | 1 | 1 | 12
Tenjam - White | 2026-01-16 | Cindy | SD4 | 23 | D4 | 6:00 | 8:50 | 122 | 2.8333 | 2.8333 | 43.0588
Tenjam - White | 2026-01-16 | Cindy | SD4 | 23 | D4 | 9:00 | 11:00 | 43 | 2 | 2 | 21.5
Tenjam - White | 2026-01-16 | Cindy | SD4 | 23 | D4 | 11:35 | 12:30 | 31 | 0.91667 | 0.91667 | 33.8182
Tenjam - White | 2026-01-16 | Cindy | SD5 | 24 | D5 | 12:30 | 13:30 | 25 | 1 | 1 | 25
Tenjam - White | 2026-01-16 | Cindy | SD5 | 24 | D5 | 13:40 | 15:30 | 106 | 1.8333 | 1.8333 | 57.8182
Tenjam - White | 2026-01-16 | Cindy | SD4 | 23 | D4 | 15:30 | 16:30 | 42 | 1 | 1 | 42
Tenjam - White | 2026-01-16 | Oralia R | SD3 | 22 | D3 | 6:00 | 7:30 | 40 | 1.5 | 1.5 | 26.6667
Tenjam - White | 2026-01-16 | Oralia R | SC3 | 14 | C3 | 7:30 | 8:30 | 78 | 1 | 1 | 78
Tenjam - White | 2026-01-16 | Oralia R | SC7 | 18 | C7 | 8:30 | 11:00 | 233 | 2.5 | 2.5 | 93.2
Tenjam - White | 2026-01-16 | Oralia R | SC7 | 18 | C7 | 11:35 | 12:20 | 167 | 0.75 | 0.75 | 222.6667
Tenjam - White | 2026-01-16 | Oralia R | SD3 | 22 | D3 | 12:30 | 15:20 | 52 | 2.8333 | 2.8333 | 18.3529
Tenjam - White | 2026-01-16 | Oralia R | SD3 | 22 | D3 | 15:20 | 16:30 | 38 | 1.1667 | 1.1667 | 32.5714
Tenjam - White | 2026-01-17 | Jackie | SD7 | 26 | D7 | 6:00 | 11:00 | 65 | 5 | 5 | 13
Tenjam - White | 2026-01-17 | Oralia S | SD5 | 24 | D5 | 6:00 | 8:50 | 120 | 2.8333 | 2.8333 | 42.3529
Tenjam - White | 2026-01-17 | Oralia S | SD5 | 24 | D5 | 9:00 | 9:30 | 25 | 0.5 | 0.5 | 50
Tenjam - White | 2026-01-17 | Oralia S | SD7 | 26 | D7 | 9:30 | 11:00 | 60 | 1.5 | 1.5 | 40
Tenjam - White | 2026-01-17 | Maricela | SD7 | 26 | D7 | 8:00 | 11:00 | 66 | 3 | 3 | 22
Tenjam - White | 2026-01-17 | Maricela | SD8 | 27 | D8 | 11:00 | 11:30 | 35 | 0.5 | 0.5 | 70
Tenjam - White | 2026-01-17 | Maricela | IFA | 28 | A | 11:30 | 12:00 | 41 | 0.5 | 0.5 | 82
Tenjam - White | 2026-01-17 | Oralia R | SD7 | 26 | D7 | 6:00 | 9:40 | 31 | 3.6667 | 3.6667 | 8.4545
Tenjam - White | 2026-01-17 | Oralia R | IFA | 28 | A | 9:40 | 11:00 | 90 | 1.3333 | 1.3333 | 67.5
Tenjam - White | 2026-01-17 | Oralia R | SD8 | 27 | D8 | 11:00 | 12:00 | 9 | 1 | 1 | 9
Tenjam - White | 2026-01-17 | Angelica | SD7 | 26 | D7 | 6:00 | 8:50 | 66 | 2.8333 | 2.8333 | 23.2941
Tenjam - White | 2026-01-17 | Angelica | SD7 | 26 | D7 | 9:00 | 11:00 | 50 | 2 | 2 | 25
Tenjam - White | 2026-01-17 | Angelica | IFA | 28 | A | 11:00 | 12:00 | 35 | 1 | 1 | 35
Tenjam - White | 2026-01-17 | Cindy | SD5 | 24 | D5 | 6:00 | 8:50 | 97 | 2.8333 | 2.8333 | 34.2353
Tenjam - White | 2026-01-17 | Cindy | SD5 | 24 | D5 | 9:00 | 9:50 | 20 | 0.83333 | 0.83333 | 24
Tenjam - White | 2026-01-17 | Cindy | SD7 | 26 | D7 | 9:55 | 10:20 | 5 | 0.41667 | 0.41667 | 12
Tenjam - White | 2026-01-17 | Cindy | IFA | 28 | A | 10:20 | 12:00 | 50 | 1.6667 | 1.6667 | 30
Tenjam - White | 2026-01-17 | Patty | SD8 | 27 | D8 | 6:00 | 8:50 | 52 | 2.8333 | 2.8333 | 18.3529
Tenjam - White | 2026-01-17 | Patty | SD8 | 27 | D8 | 9:00 | 11:45 | 58 | 2.75 | 2.75 | 21.0909
Tenjam - White | 2026-01-17 | Pilar | IFA | 28 | A | 6:00 | 7:30 | 87 | 1.5 | 1.5 | 58
Tenjam - White | 2026-01-17 | Pilar | IFB | 29 | B | 7:30 | 8:50 | 87 | 1.3333 | 1.3333 | 65.25
Tenjam - White | 2026-01-17 | Pilar | IFA | 28 | A | 9:00 | 9:15 | 11 | 0.25 | 0.25 | 44
Tenjam - White | 2026-01-17 | Pilar | IFB | 29 | B | 9:15 | 9:30 | 11 | 0.25 | 0.25 | 44
Tenjam - White | 2026-01-17 | Pilar | IFA | 28 | A | 9:42 | 10:42 | 70 | 1 | 1 | 70
Tenjam - White | 2026-01-17 | Pilar | IFB | 29 | B | 10:42 | 11:55 | 70 | 1.2167 | 1.2167 | 57.5342
Tenjam - White | 2026-01-17 | Fransico | IFA | 28 | A | 6:00 | 8:50 | 65 | 2.8333 | 2.8333 | 22.9412
Tenjam - White | 2026-01-17 | Fransico | IFA | 28 | A | 9:00 | 12:00 | 70 | 3 | 3 | 23.3333
Tenjam - Blue | 2026-01-17 | Julieta | IFC |  | C | 6:00 | 7:25 | 200 | 1.4167 | 1.4167 | 141.1765
Tenjam - Blue | 2026-01-17 | Julieta | IFD |  | D | 7:25 | 8:50 | 200 | 1.4167 | 1.4167 | 141.1765
Tenjam - White | 2026-01-17 | Julieta | IFC |  | C | 9:00 | 10:30 | 192 | 1.5 | 1.5 | 128
Tenjam - White | 2026-01-17 | Julieta | IFD |  | D | 10:30 | 12:00 | 192 | 1.5 | 1.5 | 128

## Work Steps
Dependency | Dependency Type | Task ID | FB Task ID | Category | Component | Task | Time (sec/piece) | Equipment Code
|  | CFA1 | 1 | Cutting Dept. | Fabric | Cut Fabric | 90 | CA
|  | CTA1 | 2 | Cutting Dept. | Trim | Cut Velcro | 2 | CMIS
CFA1 | FINISH | PSA1 | 3 | Prep Work | Fabric | Sew flag on panel | 7 | STS
CFA1, CTA1 | FINISH | SA1 | 4 | Sewing Dept. | A1. Small Velcro Pocket | Hem short edge | 20 | STS
SA1 | FINISH | SA2 | 5 | Sewing Dept. | A2. Small Velcro Pocket | Sew hook velcro | 25 | STS
CFA1, CTA1 | FINISH | SB1 | 6 | Sewing Dept. | B1. Connector Strap | Sew the panel together along the long sides | 12 | STS
SB1 | START | SB2 | 7 | Sewing Dept. | B2. Connector Strap | Turn inside out | 60 | FCL
SB2 | FINISH | SB3 | 8 | Sewing Dept. | B3. Connector Strap | Sew the 2 long sides of the connector Strap panel | 25 | STS
SA2, SB3 | FINISH | SB4 | 9 | Sewing Dept. | B4. Connector Strap | Sew the connector strap to the small Velcro pocket, add the loop Velcro. | 35 | STS
SB4 | FINISH | SB5 | 10 | Sewing Dept. | B5. Connector Strap | Close the sides of the small Velcro pocket. | 15 | STS
SB5 | START | SB6 | 11 | Sewing Dept. | B6. Connector Strap | Cut threads, Turn right side out, Cut corners | 25 | FCL
CFA1, CTA1 | FINISH | SC1 | 12 | Sewing Dept. | C1. Hanging Big Pocket | Hem one short side | 17 | STS
SC1 | FINISH | SC2 | 13 | Sewing Dept. | C2. Hanging Big Pocket | Fold to the marking, and close both sides | 35 | STS
SC2 | FINISH | SC3 | 14 | Sewing Dept. | C3. Hanging Big Pocket | Add stitching to the lower corners to create volume | 36 | STS
SC3 | START | SC4 | 15 | Sewing Dept. | C4. Hanging Big Pocket | Turn right side out | 25 | FCL
SC4 | FINISH | SC5 | 16 | Sewing Dept. | C5. Hanging Big Pocket | Add straight single-stitching to the top of the pocket | 15 | STS
SC5 | FINISH | SC6 | 17 | Sewing Dept. | C6. Hanging Big Pocket | Sew the center stitch | 20 | STS
SC6 | FINISH | SC7 | 18 | Sewing Dept. | C7. Bartack | Add the bartack to the top of the hanging big pocket | 14 | SBT
SC7 | FINISH | SC8 | 19 | Sewing Dept. | C8. Hanging Big Pocket | Stitch the connector strap to the large pocket | 9 | STS
CFA1, CTA1, PSA1 | FINISH | SD1 | 20 | Sewing Dept. | D1. Cushion Cover | Sew the zipper onto the left panel with USA flag. | 100 | STS
CFA1, CTA1 | FINISH | SD2 | 21 | Sewing Dept. | D2. Cushion Cover | Sew the zipper with hemming foot onto the right panel without the flag | 30 | STSZF
SD1, SD2 | START | SD3 | 22 | Sewing Dept. | D3. Cushion Cover | Cut extra material off add the zipper pull | 18 | FCL
SD3 | FINISH | SD4 | 23 | Sewing Dept. | D4. Cushion Cover | Add stitch to both zipper ends | 60 | STS
SD4 | FINISH | SD5 | 24 | Sewing Dept. | D5. Cushion Cover | Sew the long sides closed | 30 | STS
SD5 | FINISH | SD6 | 25 | Sewing Dept. | D6.Cushion Cover | Sew front panel with pockets to zipper panel | 30 | STS
SD6 | FINISH | SD7 | 26 | Sewing Dept. | D7. Cushion Cover | Sew on the side panels | 30 | STS
SD7 | FINISH | SD8 | 27 | Sewing Dept. | D8. Cushion Cover | Turn right side out | 30 | FCL
SD7 | FINISH | IFA | 28 | Inspection | A. Inspection Quality | Clean and inspect for any loose threads, missing, flag, ect. | 30 | FCL
IFA | FINISH | IFB | 29 | Inspection | B. Inspection Insert Foam | Insert foam piece into the headrest. | 50 | FCL
IFB | FINISH | IFC | 30 | Inspection | C. Inspection Bag | Individually bagged into poly bag S-1997 Size: 9 x 24 | 30 | FCL
IFC | FINISH | IFD | 31 | Inspection | D. Inspection Pack | Pack into cartons | 60 | PAC

## BOM Trsfm
Step Number | Department | Step
1 | Cutting Dept. | Auto Cutter | Cut Fabric | Auto CutterCut Fabric
2 | Sewing Dept. | Pre-Step | Cut Velcro | Pre-Step Cut Velcro
3 | Sewing Dept. | Pre-Step | Sew flag on panel | Pre-Step Sew flag on panel
4 | Sewing Dept. | A1. Small Velcro Pocket | Hem short edge | A1. Small Velcro Pocket Hem short edge
5 | Sewing Dept. | A2. Small Velcro Pocket | Sew hook velcro | A2. Small Velcro Pocket Sew hook velcro
6 | Sewing Dept. | B1. Connector Strap | Sew the panel together along the long sides | B1. Connector Strap Sew the panel together along the long sides
7 | Sewing Dept. | B2. Connector Strap | Turn inside out | B2. Connector Strap Turn inside out
8 | Sewing Dept. | B3. Connector Strap | Sew the 2 long sides of the connector Strap panel | B3. Connector Strap Sew the 2 long sides of the connector Strap panel
9 | Sewing Dept. | B4. Connector Strap | Sew the connector strap to the small Velcro pocket, add the loop Velcro. | B4. Connector Strap Sew the connector strap to the small Velcro pocket, add the loop Velcro.
10 | Sewing Dept. | B5. Connector Strap | Close the sides of the small Velcro pocket. | B5. Connector Strap Close the sides of the small Velcro pocket.
11 | Sewing Dept. | B6. Connector Strap | Cut threads, Turn right side out, Cut corners | B6. Connector Strap Cut threads, Turn right side out, Cut corners
12 | Sewing Dept. | C1. Hanging Big Pocket | Hem one short side | C1. Hanging Big Pocket Hem one short side
13 | Sewing Dept. | C2. Hanging Big Pocket | Fold to the marking, and close both sides | C2. Hanging Big Pocket Fold to the marking, and close both sides
14 | Sewing Dept. | C3. Hanging Big Pocket | Add stitching to the lower corners to create volume | C3. Hanging Big Pocket Add stitching to the lower corners to create volume
15 | Sewing Dept. | C4. Hanging Big Pocket | Turn right side out | C4. Hanging Big Pocket Turn right side out
16 | Sewing Dept. | C5. Hanging Big Pocket | Add straight single-stitching to the top of the pocket | C5. Hanging Big Pocket Add straight single-stitching to the top of the pocket
17 | Sewing Dept. | C6. Hanging Big Pocket | Sew the center stitch | C6. Hanging Big Pocket Sew the center stitch
18 | Sewing Dept. | C7. Bartack | Add the bartack to the top of the hanging big pocket | C7. Bartack Add the bartack to the top of the hanging big pocket
19 | Sewing Dept. | C8. Hanging Big Pocket | Stitch the connector strap to the large pocket | C8. Hanging Big Pocket Stitch the connector strap to the large pocket
20 | Sewing Dept. | D1. Cushion Cover | Sew the zipper onto the left panel with USA flag. | D1. Cushion Cover Sew the zipper onto the left panel with USA flag.
21 | Sewing Dept. | D2. Cushion Cover | Sew the zipper with hemming foot onto the right panel without the flag | D2. Cushion Cover Sew the zipper with hemming foot onto the right panel without the flag
22 | Sewing Dept. | D3. Cushion Cover | Cut extra material off add the zipper pull | D3. Cushion Cover Cut extra material off add the zipper pull
23 | Sewing Dept. | D4. Cushion Cover | Add stitch to both zipper ends | D4. Cushion Cover Add stitch to both zipper ends
24 | Sewing Dept. | D5. Cushion Cover | Sew the long sides closed | D5. Cushion Cover Sew the long sides closed
25 | Sewing Dept. | D6.Cushion Cover | Sew front panel with pockets to zipper panel | D6.Cushion Cover Sew front panel with pockets to zipper panel
26 | Sewing Dept. | D7. Cushion Cover | Sew on the side panels | D7. Cushion Cover Sew on the side panels
27 | Sewing Dept. | D8. Cushion Cover | Turn right side out | D8. Cushion Cover Turn right side out
28 | Inspection | A. Inspection Quality | Clean and inspect for any loose threads, missing, flag, ect. | A. Inspection Quality Clean and inspect for any loose threads, missing, flag, ect.
29 | Inspection | B. Inspection Insert Foam | Insert foam piece into the headrest. | B. Inspection Insert Foam Insert foam piece into the headrest.
30 | Inspection | C. Inspection Bag | Individually bagged into poly bag S-1997 Size: 9 x 24 | C. Inspection Bag Individually bagged into poly bag S-1997 Size: 9 x 24
31 | Inspection | D. Inspection Pack | Pack into cartons | D. Inspection Pack Pack into cartons

## BOMInstructions
SI JACOBSON MANUFACTURING
BOM Instructions
Order | Name | Description | Details |  | URL
1 | Cutting Dept. | Auto Cutter | 25JAM001_Tenjam Headrest_Cut File.Project |  | URL
2 | Sewing Dept. | Pre-Step / Cut Velcro | Cut the Velcro pieces. Corta las piezas de velcro.
3 | Sewing Dept. | Pre-Step / Sew flag on panel | Sew the USA flag onto the fabric panel. Cose la bandera de Estados Unidos al panel de tela.
4 | Sewing Dept. | A1. Small Velcro Pocket / Hem short edge | Hem the short edges Dobladillar los bordes cortos
5 | Sewing Dept. | A2. Small Velcro Pocket / Sew hook velcro | Sew on the hook Velcro. Cose el velcro de gancho
6 | Sewing Dept. | B1. Connector Strap / Sew the panel together along the long sides | Sew the panel together along the long sides Cose los paneles juntos a lo largo de los lados largos.
7 | Sewing Dept. | B2. Connector Strap / Turn inside out | Turn inside-out Dale la vuelta
8 | Sewing Dept. | B3. Connector Strap / Sew the 2 long sides of the connector Strap panel | Sew the 2 long sides of the connector strap panel Cose los dos lados largos del panel de conexión.
9 | Sewing Dept. | B4. Connector Strap /Sew the connector strap to the small Velcro pocket, add the loop Velcro. | Sew the connector strap to the small Velcro pocket, add the loop Velcro. Cose la correa de conexión al pequeño bolsillo de velcro y añade la tira de velcro.
10 | Sewing Dept. | B5. Connector Strap / Close the sides of the small Velcro pocket. | Close the sides of the small Velcro pocket. Cierra los lados del pequeño bolsillo de velcro.
11 | Sewing Dept. | B6. Connector Strap / Cut threads, Turn right side out, Cut corners | Cut threads, Turn right side out, Cut corners Corta los hilos, dale la vuelta al derecho, corta las esquinas.
12 | Sewing Dept. | C1. Hanging Big Pocket / Hem one short side | Hem one short side
January 14, 2026 8:42:15 AM CST |  |  |  | Page 1 of |  | 4
SI JACOBSON MANUFACTURING
BOM Instructions
Order | Name | Description | Details |  | URL
Dobladillar un lado corto
13 | Sewing Dept. | C2. Hanging Big Pocket / Fold to the marking, and close both sides | Fold to the marking, and close both sides Doblar hasta la marca y cerrar ambos lados
14 | Sewing Dept. | C3. Hanging Big Pocket / Add stitching to the lower corners to create volume | Add stitching to the lower corners to create volume Añadir costuras en las esquinas inferiores para dar volumen
15 | Sewing Dept. | C4. Hanging Big Pocket / Turn right side out | Turn right side out darle la vuelta
16 | Sewing Dept. | C5. Hanging Big Pocket / Add straight single-stitching to the top of the pocket | Add straight single-stitching to the top of the pocket Añadir una costura recta simple en la parte superior del bolsillo
17 | Sewing Dept. | C6. Hanging Big Pocket / Sew the center stitch | Sew the center stitch Coser la costura central
18 | Sewing Dept. | C7. Bartack / Add the bartack to the top of the hanging big pocket | Add the bartack to the top of the hanging big pocket Añada la puntada de refuerzo a la parte superior del bolsillo grande colgante.
19 | Sewing Dept. | C8. Hanging Big Pocket / Stitch the connector strap to the large pocket | Stitch the connector strap to the large pocket Coser la correa de conexión al bolsillo grande
20 | Sewing Dept. | D1. Cushion Cover /Sew the zipper onto the left panel with USA flag. | Sew the zipper onto the left panel with USA flag. Cose la cremallera al panel izquierdo con la bandera de Estados Unidos.
21 | Sewing Dept. | D2. Cushion Cover / Sew the zipper with hemming foot onto the right panel without the flag | Sew the zipper with hemming foot onto the right panel without the flag Cose la cremallera con el prensatelas para dobladillos en el panel derecho, sin la bandera.
January 14, 2026 8:42:15 AM CST |  |  |  | Page 2 of |  | 4
SI JACOBSON MANUFACTURING
BOM Instructions
Order | Name | Description | Details |  | URL
22 | Sewing Dept. | D3. Cushion Cover / Cut extra material off add the zipper pull | Cut extra material off add the zipper pull Corta el material sobrante y añade el tirador de la cremallera.
23 | Sewing Dept. | D4. Cushion Cover / Add stitch to both zipper ends | Add stitch to both zipper ends Añada una puntada a ambos extremos de la cremallera.
24 | Sewing Dept. | D5. Cushion Cover / Sew the long sides closed | Sew the long sides closed Cose los lados largos.
25 | Sewing Dept. | D6.Cushion Cover / Sew front panel with pockets to zipper panel | Sew front panel with pockets to zipper panel Cose el panel frontal con los bolsillos al panel de la cremallera.
26 | Sewing Dept. | D7. Cushion Cover / Sew on the side panels | Sew on the side panels Cose los paneles laterales.
27 | Sewing Dept. | D8. Cushion Cover / Turn right side out | Turn right side out Dale la vuelta
28 | Inspection | A. Inspection Quality / Clean and inspect for any loose threads, missing, flag, ect. | Clean and inspect for any loose threads, missing, flag, ect. Limpie e inspeccione para detectar hilos sueltos, piezas faltantes, banderas, etc.
29 | Inspection | B. Inspection Insert Foam / Insert foam piece into the headrest. | Insert foam piece into the headrest. Inserte la pieza de espuma en el reposacabezas.
30 | Inspection | C. Inspection Bag / Individually bagged into poly bag S-1997 Size: 9 x 24 | Individually bagged into poly bag S-1997 Size: 9 x 24 Empaquetado individualmente en bolsa de polietileno S-1997. Tamaño: 9 x 24
31 | Inspection | D. Inspection Pack / Pack into cartons S-4739 Size: 20 x 24 x 16 Pack 3 row of 8 for a total of 24 pieces per carton | Pack into cartons S-4739 Size: 20 x 24 x 16 Pack 3 row of 8 for a total of 24 pieces per carton Empaquetado en cajas de cartón S-4739. Tamaño: 20 x 24 x 16
January 14, 2026 8:42:15 AM CST |  |  |  | Page 3 of |  | 4
SI JACOBSON MANUFACTURING
BOM Instructions
Order | Name | Description | Details |  | URL
Se colocan 3 filas de 8 unidades, para un total de 24 piezas por caja.
January 14, 2026 8:42:15 AM CST |  |  |  | Page 4 of |  | 4

## Equip Matrix
Equipment Count | Work Code | Work Type | Obet | Temp - Noe | Temp - Fransisco | Pilar | Patty | Oralia S | Norma | Oralia R | Maricella | Angelica | Jackie | Cyndi | Julieta
100 | CTL | Cutting - Team Lead | Y
1 | CMA | Cutting - Manual | Y
1 | CA | Cutting - Automated Skilled | Y | [10 empty] | Y
100 | CAU | Cutting - Automated Unskilled | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | Y
1 | CMIS | Cutting - Miscellaneous | Y |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
2 | ESU | Embellishment Silkscreening - UV |  |  |  | Y | Y
2 | ESH | Embellishment Silkscreening - Heat |  |  |  | Y | Y
100 | ESC | Embellishment Silkscreening - Catching | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | Y
100 | ASTL | Auto Sewing - Team Lead | [5 empty] | Y
2 | ASL | Auto Sewing - Large | [5 empty] | Y | [6 empty] | Y
1 | ASM | Auto Sewing - Medium | [5 empty] | Y | [6 empty] | Y
1 | ASS | Auto Sewing - Small | [5 empty] | Y | [6 empty] | Y
100 | STL | Sewing - Team Lead | [6 empty] | Y
5 | STS | Sewing - Top Stitch Single Needle | [5 empty] | Y | Y | Y | Y | Y | Y | Y
2 | STD | Sewing - Top Stitch Double Needle | [5 empty] | Y | Y | Y | Y | Y | Y | Y
1 | STSZF | Sewing - Top Stitch Single Needle Zipper Foot | [5 empty] | Y | Y | Y | Y | Y | Y | Y
2 | SBT | Sewing - Bar Tac | [5 empty] | Y | Y | Y | Y | Y | Y | Y
1 | SZZ | Sewing - Zigzag | [5 empty] | Y | Y | Y | Y | Y | Y | Y
1 | FR | Finishing - Rivet |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
1 | FG | Finishing - Grommet |  |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
100 | FCL | Finishing - cleanup | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
100 | QCO | Quality Control Outgoing | Y |  |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
100 | PAC | Packing | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
100 | WRE | Warehouse - Receiving | Y | Y | Y
100 | WIQC | Warehouse - Incoming Quality Control | Y
1 | WFL | Warehouse - Forklift | Y |  |  |  |  | Y
100 | WOP | Warehouse - Order Picking | Y | Y | Y
100 | WCC | Warehouse - Cycle Counting | Y | Y | Y
100 | WS | Warehouse - Shipping | Y | Y | Y
100 Signifies equipment is not needed
Automated Cutting requires 2 people…Skilled Operator and Unskilled
Embellishment Silk Screen requires 2 people 1 skilled and 1 unskilled
If work is being done in a particular department, Team lead has to be there. For sewing, team lead is supervising, helping, training, etc. Not sewing